Drink Awareness App Roadmap Eight phases from research to portfolio-ready MVP — 18 May to 18 October 2026.

| Document | Roadmap |
| --- | --- |
| Version | v2.0 |
| Date | 8 June 2026 |
| Author | Matthew Reid |
| Project | Drink Awareness App |
| Status | Final Draft |

Table of Contents

Executive Summary	2

1.  Roadmap Purpose	2

2.  Roadmap Overview	2

3.  Roadmap Principles	3

4.  Project Summary Timeline	3

5.  Phase 1 — Research and Validation	4

6.  Phase 2 — Planning and Backlog	4

7.  Phase 3 — UX/UI Design	5

8.  Phase 4 — Technical Setup	5

9.  Phase 5 — Core Feature Build	6

10. Phase 6 — Polish, Testing and Iteration	6

11. Phase 7 — Deployment Prep	7

12. Phase 8 — MVP Deployment and Portfolio Release	7

13. Milestone Summary	8

14. Documentation Deliverables	8

15. MVP Feature Delivery Plan	9

16. Risks and Contingency	9

17. Success Criteria	10

18. Summary	10

Executive Summary

This roadmap defines the planned development path for the Drink Awareness App from 18 May 2026 to 18 October 2026. The project is structured across eight phases: Research and Validation, Planning and Backlog, UX/UI Design, Technical Setup, Core Feature Build, Polish and Testing, Deployment Prep, and MVP Deployment. Each phase has a defined date range, set of activities and expected outputs. The milestone summary in Section 13 provides a single-page view of all nine key milestones and their target dates. The roadmap is designed to be used alongside all other project documents, which are cross-referenced in Section 14. The project is currently in Phase 1. Phase 2 (Planning and Backlog) begins 1 June 2026.

# 1.  Roadmap Purpose

The purpose of this roadmap is to outline the planned project timeline for the Drink Awareness App. It breaks the project into clear phases, identifies the main activities for each phase, and defines the key outputs expected before the MVP is ready for demonstration and portfolio use.

The roadmap is intended to keep the project realistic, organised and focused. It should be used alongside the product brief, research plan, interview questions, MVP scope, feature backlog, competitor analysis, and assumptions and risks spreadsheet.

# 2.  Roadmap Overview

Drink Awareness App is a planned mobile app for iOS and Android that helps adults aged 18+ discover pubs and bars, view venue details, browse drink menus and prices, manually log drinks, review daily and weekly summaries, and receive AI-generated insights to support healthier drinking awareness.

The roadmap starts from the project start date of 18 May 2026 and works towards an MVP deployment and portfolio-ready release by 18 October 2026 — a total of five months across eight structured phases.

# 3.  Roadmap Principles

The roadmap will be guided by the following principles:

- Keep the MVP focused on the agreed core features at all times.

- Validate assumptions before committing to complex build decisions.

- Prioritise responsible design because the app relates to alcohol awareness.

- Use sample or limited venue and menu data where live integrations are not practical for the MVP.

- Build in small, testable stages rather than attempting all features at once.

- Keep documentation and GitHub commits up to date throughout the project.

- Treat later features as future expansion rather than first-build requirements.

# 4.  Project Summary Timeline

|  | Date Range | Phase | Focus | Status |
| --- | --- | --- | --- | --- |
| 1 | 18 May – 31 May 2026 | Research and Validation | Validate the problem, review competitors, collect user feedback and confirm MVP direction. | In Progress |
| 2 | 1 Jun – 14 Jun 2026 | Planning and Backlog | Convert research findings into a prioritised backlog and development plan. | Not Started |
| 3 | 15 Jun – 28 Jun 2026 | UX/UI Design | Design core screens, user flows and visual direction. | Not Started |
| 4 | 29 Jun – 12 Jul 2026 | Technical Setup | Prepare app structure, environment, data model and sample data. | Not Started |
| 5 | 13 Jul – 23 Aug 2026 | Core Feature Build | Build all must-have MVP features in priority order. | Not Started |
| 6 | 24 Aug – 20 Sep 2026 | Polish, Testing and Iteration | Test, fix issues, improve usability and reach a stable MVP. | Not Started |
| 7 | 21 Sep – 4 Oct 2026 | Deployment Prep | Prepare for release: checklist, README, screenshots and demo data. | Not Started |
| 8 | 5 Oct – 18 Oct 2026 | MVP Deployment and Release | Complete the MVP and prepare portfolio-ready evidence. | Not Started |

# 5.  Phase 1 — Research and Validation

| P1 | Research and Validation 18 May – 31 May 2026 |
| --- | --- |

This phase focuses on validating the app idea before deeper planning and design work begins. The aim is to understand whether the problem is meaningful, whether the proposed MVP features are useful, and whether the app can be positioned responsibly.

| Activity | Description | Output |
| --- | --- | --- |
| Finalise early documentation | Complete and review the product brief, research plan, interview questions and MVP scope. | Clean v1.0 documentation set. |
| Competitor research | Review alcohol tracking, venue discovery, habit tracking and AI insight tools. | Competitor analysis notes and spreadsheet inputs. |
| User feedback | Collect early feedback using interview questions and/or a short survey. | User research notes and key patterns. |
| Assumption testing | Check whether users value manual logging, venue discovery, summaries and AI insights. | Updated assumptions and risks register. |
| MVP validation | Use findings to confirm or refine the MVP scope before planning begins. | Inputs for backlog and planning phase. |

# 6.  Phase 2 — Planning and Backlog

| P2 | Planning and Backlog 1 June – 14 June 2026 |
| --- | --- |

This phase turns the research and MVP scope into a practical plan for design and development. The main goal is to produce a prioritised backlog and ensure the project has clear requirements before the UX/UI design phase begins.

| Activity | Description | Output |
| --- | --- | --- |
| Review research findings | Summarise key user needs, concerns and feature priorities from research phase. | Research summary and decision notes. |
| Create feature backlog | Break MVP features into smaller user stories or development tasks. | docs/feature-backlog.xlsx |
| Update assumptions and risks | Track uncertain areas such as manual logging, venue data and AI insight value. | docs/assumptions-risks.xlsx |
| Prioritise requirements | Separate must-have, should-have, could-have and out-of-scope items. | Prioritised MVP backlog. |
| Define next tasks | Prepare a clear sequence of work for the design and technical setup phases. | Planning checklist. |

# 7.  Phase 3 — UX/UI Design

| P3 | UX/UI Design 15 June – 28 June 2026 |
| --- | --- |

This phase defines how the app will look and feel. The design should support quick use during social outings, make summaries easy to understand at a glance, and use a calm, non-judgemental tone throughout.

| Design Area | Purpose | Expected Output |
| --- | --- | --- |
| User journey | Map the main flow from opening the app to logging drinks and viewing summaries. | Core user journey diagram and flow notes. |
| Screen list | Identify all screens required for the MVP. | Home, venue list/map, venue details, drink menu, log drink, daily summary, weekly summary and insights screens. |
| Wireframes | Sketch low-fidelity layouts for each main screen. | Complete wireframe set. |
| Visual direction | Choose a design style suitable for health awareness and social use. | Colour, typography and layout direction. |
| Responsible wording | Plan how the app communicates alcohol awareness without judgement. | Example copy for insights, summaries and disclaimers. |

# 8.  Phase 4 — Technical Setup

| P4 | Technical Setup 29 June – 12 July 2026 |
| --- | --- |

This phase prepares the technical foundation for the app. The aim is to create a clean project structure, confirm the development approach, and prepare the basic data model before feature development begins.

| Area | Description | Output |
| --- | --- | --- |
| Development environment | Set up the mobile app development environment and confirm the framework and tools to be used. | Working development setup. |
| Project structure | Create the initial app structure with organised folders and naming conventions. | Initial app skeleton. |
| Data model | Define basic structures for venues, drink menus, drink logs, summaries and insights. | Initial data model documented. |
| Sample data | Create realistic sample venues and drink menu items for MVP demonstration. | Sample venue and menu dataset. |
| Repository hygiene | Keep commits small and meaningful as technical setup progresses. | Clean, readable GitHub history. |

# 9.  Phase 5 — Core Feature Build

| P5 | Core Feature Build 13 July – 23 August 2026 |
| --- | --- |

This is the main development phase. Features must be built in the order below to support a working end-to-end user journey as early as possible — starting with navigation and data foundations before summaries and insights.

| # | Feature Area | Outcome |
| --- | --- | --- |
| 1 | App navigation and home screen | Users can open the app and understand its main purpose. |
| 2 | Venue discovery | Users can browse and search example venues using a list and/or map screen. |
| 3 | Venue details | Users can open a venue and view its basic information. |
| 4 | Drink menus and prices | Users can view sample drink items, sizes, ABV and prices. |
| 5 | Manual drink logging | Users can log drinks quickly using required and optional fields. |
| 6 | Daily summary | Users can see all drinks logged for the current day. |
| 7 | Weekly summary | Users can see basic weekly totals and patterns. |
| 8 | AI-generated insights | Users receive a supportive insight based on their logged data. |
| 9 | Responsible design checks | All screens avoid judgemental wording, medical claims and gamified consumption. |

# 10. Phase 6 — Polish, Testing and Iteration

| P6 | Polish, Testing and Iteration 24 August – 20 September 2026 |
| --- | --- |

This phase focuses on making the MVP stable, understandable and suitable for demonstration. Testing should cover functionality, usability, data accuracy and responsible design wording.

| Testing Area | Purpose | Example Checks |
| --- | --- | --- |
| Functional testing | Confirm that each core feature works as expected. | Venue browsing, drink logging, summary updates and insight display all working. |
| Usability testing | Check that the app is quick and easy to use in practice. | Can a user log a drink without confusion or assistance? |
| Data testing | Confirm logged data is stored and summarised correctly. | Daily and weekly totals update correctly after each new log entry. |
| Responsible design review | Check that the app avoids risky or judgemental wording. | No leaderboards, no medical claims and no encouragement to drink more. |
| Bug fixing | Resolve all issues found during testing. | Stable, demonstrable MVP candidate achieved. |

# 11. Phase 7 — Deployment Prep

| P7 | Deployment Prep 21 September – 4 October 2026 |
| --- | --- |

This phase prepares the project for release or demonstration. The priority is to ensure the app, repository and supporting documentation are clear enough for portfolio use.

| Preparation Area | Description | Output |
| --- | --- | --- |
| Release checklist | Confirm the MVP is stable and all acceptance criteria from doc 04 are met. | Signed-off deployment readiness checklist. |
| Demo data | Prepare sample venues, drinks and logs to demonstrate the app clearly. | Clean and realistic demo dataset. |
| Screenshots | Capture key screens for the README and portfolio presentation. | Full app screenshot set. |
| README update | Explain project purpose, features, setup instructions and current status. | Updated and complete GitHub README. |
| Repository review | Check folder structure, commit quality and documentation completeness. | Portfolio-ready GitHub repository. |

# 12. Phase 8 — MVP Deployment and Portfolio Release

| P8 | MVP Deployment and Portfolio Release 5 October – 18 October 2026 |
| --- | --- |

This final phase completes the MVP and prepares it as a portfolio-ready project. The aim is to present a coherent app concept, a working MVP, clear documentation and a professional development process.

| Activity | Description | Output |
| --- | --- | --- |
| Final MVP checks | Confirm the end-to-end user journey works from venue discovery to AI insights. | Final tested and signed-off MVP. |
| Portfolio write-up | Prepare a short explanation of the project, problem, features and learning outcomes. | Portfolio project summary. |
| Final documentation review | Ensure all docs are complete, consistent and saved correctly in the docs folder. | Clean and complete documentation set. |
| GitHub finalisation | Ensure the full repository is pushed, readable and well-structured. | Portfolio-ready GitHub repository. |
| Future work notes | Record later features that can be developed after the MVP phase. | Post-MVP roadmap notes. |

# 13. Milestone Summary

| Milestone | Target Date | Completion Evidence |
| --- | --- | --- |
| Documentation baseline complete | 31 May 2026 | Product brief, research plan, interview questions, MVP scope and roadmap all at v1.0. |
| Research and validation complete | 31 May 2026 | Research findings, competitor notes and updated assumptions documented. |
| Planning and backlog complete | 14 June 2026 | Feature backlog and assumptions/risks spreadsheet updated and prioritised. |
| UX/UI design complete | 28 June 2026 | Wireframes and screen flow prepared and reviewed. |
| Technical setup complete | 12 July 2026 | App project structure, data model and sample data prepared. |
| Core MVP feature build complete | 23 August 2026 | All must-have features working end to end. |
| Testing and polish complete | 20 September 2026 | Stable MVP candidate achieved with test notes documented. |
| Deployment prep complete | 4 October 2026 | README, screenshots and release checklist ready. |
| Portfolio-ready MVP complete | 18 October 2026 | Final MVP and all documentation ready to present. |

# 14. Documentation Deliverables

The docs folder acts as the project knowledge base. All documents below should be kept up to date throughout the project.

| Document | Purpose | Timing |
| --- | --- | --- |
| 00-project-index.md | Overview of the project documents and repository structure. | Maintain throughout project. |
| 01-product-brief.docx | Defines the app idea, problem, target users, MVP and business model. | Drafted at project start. |
| 02-research-plan.docx | Defines the research and validation approach. | Drafted during Phase 1. |
| 03-interview-questions.docx | Structured questions for user interviews and feedback sessions. | Drafted during Phase 1. |
| 04-mvp-scope.docx | Defines in-scope and out-of-scope MVP features and acceptance criteria. | Drafted before Phase 2. |
| 05-roadmap.docx | Defines the project timeline and phase-based plan. | This document. |
| assumptions-risks.xlsx | Tracks assumptions, risks, likelihood, impact and mitigations. | Create and update from Phase 2. |
| competitor-analysis.xlsx | Records competitor research findings. | Create and update during Phase 1. |
| feature-backlog.xlsx | Breaks MVP features into prioritised development tasks. | Create and update during Phase 2. |

# 15. MVP Feature Delivery Plan

The MVP features should be delivered in the order below to support a working end-to-end user journey as early as possible in Phase 5.

| Feature | Target Phase | Delivery Notes |
| --- | --- | --- |
| Venue discovery | Core feature build | Use sample venues first; add search, list and map behaviour as practical. |
| Venue details | Core feature build | Show venue name, location, description and example drinks. |
| Drink menus and prices | Core feature build | Use realistic sample menu data; live integrations are not required for MVP. |
| Manual drink logging | Core feature build | Prioritise quick logging with minimal required fields. |
| Daily summary | Core feature build | Update after each logged drink in real time. |
| Weekly summary | Core feature build | Show simple weekly totals and patterns. |
| AI-generated insights | Core build and polish | Start with rule-based or pattern-based examples if needed; refine during testing. |
| Responsible design wording | All phases | Review all copy throughout design, build and testing. |

# 16. Risks and Contingency

The roadmap includes contingency by keeping complex features out of the MVP and allowing sample data where live data is not practical. The table below maps each risk to its roadmap impact and planned response.

| Risk | Roadmap Impact | Contingency |
| --- | --- | --- |
| Research takes longer than planned. | Phase 2 planning and backlog may be delayed. | Use a small but useful sample of feedback; continue updating assumptions later. |
| Venue and menu data is difficult to source. | Venue features may feel incomplete or unrealistic. | Use well-structured sample data for MVP demonstration. |
| Manual logging feels too slow to use. | Core user journey may be weak or abandoned. | Reduce required fields; add quick-select common drinks during polish phase. |
| AI insights are too generic. | Insight feature may not feel valuable to users. | Use pattern-based insights and refine wording during Phase 6. |
| Build phase takes longer than expected. | Testing or deployment prep phases may be compressed. | Prioritise must-have features; postpone could-have items without hesitation. |
| Responsible design concerns emerge. | Social or insight features may need to be redesigned. | Remove or reword any risky features; keep the app focused on awareness. |

# 17. Success Criteria

By the end of the roadmap, the project should be considered successful if all of the following are true:

- The MVP clearly communicates the purpose of the Drink Awareness App.

- Users can discover example venues and view venue details.

- Users can view drink menu items and prices.

- Users can manually log drinks quickly and reliably.

- Users can view daily and weekly summaries based on logged drinks.

- Users can receive supportive AI-generated or AI-style insights.

- The app avoids medical claims and avoids encouraging excessive drinking.

- The GitHub repository contains a clear, well-structured history of project progress.

- The docs folder contains complete planning, research and scope documents.

- The final MVP is suitable for portfolio demonstration without further preparation.

# 18. Summary

This roadmap sets out the planned development path for the Drink Awareness App from 18 May 2026 to 18 October 2026. The project is structured across eight phases: Research and Validation, Planning and Backlog, UX/UI Design, Technical Setup, Core Feature Build, Polish and Testing, Deployment Prep, and MVP Deployment. Each phase has defined activities, outputs and a target completion date. The roadmap keeps the project firmly focused on the agreed MVP scope: venue discovery, venue details, drink menus and prices, manual drink logging, daily and weekly summaries, AI-generated insights and responsible design. Later features remain outside the MVP unless the roadmap is formally revised.