## Dashboard
Drink Awareness App — Assumptions & Risks Dashboard
Purpose: Track key project assumptions and risks. Update status as research, design and build work progresses.
Total Assumptions |  | Total Risks |  | High Risks | Open Risks | Validated
10 |  | 10 |  | 3 | 8 | 0
No. | Next Action | Type | Target Date
1 | Review assumptions after interviews/surveys | Due | 31 May 2026
2 | Update risk scores after competitor research | Due | 31 May 2026
3 | Move validated items into MVP scope/backlog | Due | 14 Jun 2026
4 | Review responsible design risks before UX/UI design | Due | 28 Jun 2026
5 | Re-check high risks before core build | Due | 13 Jul 2026
How to use this workbook
1. Update assumptions and risks as research, design and build work progresses.
2. Use the Status columns to show whether items are open, validated, mitigated or closed.
3. Risk Score is calculated automatically as Likelihood × Impact.
4. High risks should be reviewed before each major project phase.
5. Use the Evidence / Notes columns to record decisions from interviews and testing.
6. Keep out-of-scope features separate from MVP work to protect the timeline.

## Assumptions Register
Assumptions Register
ID | Category | Assumption | Impact if Wrong | Validation Method | Related Deliverable | Owner | Status | Review Date | Evidence / Notes
A01 | User Research | Users are willing to manually log drinks during or after social outings. | The core logging feature may not be used regularly. | Interview/survey participants about when and how they would log drinks. | 03-interview-questions.docx | Matthew Reid | Needs Review | 31 May 2026 | Validate before finalising MVP flow.
A02 | Venue/Menu Data | Venue and menu information adds value to a drink awareness app. | The app may be more complex than necessary if users only want tracking. | Ask users to rank venue discovery against logging and summaries. | 02-research-plan.docx | Matthew Reid | Needs Review | 31 May 2026 | Compare with competitor apps.
A03 | Product Scope | Sample venue and menu data is acceptable for an MVP demonstration. | The MVP may feel unrealistic without live venue data. | Use realistic sample data and test whether users understand it is an MVP. | 04-mvp-scope.docx | Matthew Reid | Needs Review | 14 Jun 2026 | Useful for keeping build achievable.
A04 | AI Insights | AI-generated insights will make the app more valuable than a basic logbook. | The AI feature may feel generic, unnecessary or untrusted. | Test example insight wording with interview participants. | 03-interview-questions.docx | Matthew Reid | Needs Review | 31 May 2026 | Keep tone supportive and non-medical.
A05 | Responsible Design | Users prefer supportive, non-judgemental feedback about drinking awareness. | Poor wording could make users feel judged or unsafe. | Ask users about preferred tone and messages to avoid. | 03-interview-questions.docx | Matthew Reid | Needs Review | 31 May 2026 | Important because app relates to alcohol.
A06 | Business Model | A freemium model is suitable for the app. | Premium features may not justify a subscription. | Ask users whether advanced insights/planning would be worth paying for. | 01-product-brief.docx | Matthew Reid | Needs Review | 14 Jun 2026 | Payment system remains out of MVP.
A07 | Timeline | The MVP can be planned, built, tested and prepared by 18 October 2026. | The release may slip if scope expands. | Review roadmap milestones after each phase. | 05-roadmap.docx | Matthew Reid | In Progress | 14 Jun 2026 | Keep later features out of scope.
A08 | Data/Privacy | Users will be comfortable logging drinks if data collection is minimal. | Privacy concerns may reduce adoption. | Ask participants what data they are comfortable sharing. | 03-interview-questions.docx | Matthew Reid | Needs Review | 31 May 2026 | Consider local/simple usage for MVP.
A09 | Product Scope | Daily and weekly summaries are enough for the first version. | Users may expect longer-term trends or charts. | Ask users what summaries they would realistically check. | 04-mvp-scope.docx | Matthew Reid | Needs Review | 14 Jun 2026 | Advanced analytics can be premium/later.
A10 | Technical | A cross-platform approach is practical for iOS and Android. | Technical complexity may increase if platform-specific features are needed. | Assess technical stack during the technical setup phase. | 05-roadmap.docx | Matthew Reid | Not Started | 12 Jul 2026 | Decision required before core build.

## Risk Register
Risk Register
ID | Category | Risk | Cause | Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Priority | Status | Mitigation | Owner | Review Date | Notes
R01 | Product Scope | MVP scope becomes too large. | Too many later features are pulled into the first build. | Development takes longer than planned and core features are not finished. | 4 | 4 | 16 | High | Open | Keep MVP features limited to must-have scope and track later ideas separately. | Matthew Reid | 14 Jun 2026 | Watch during backlog planning.
R02 | User Research | Users forget to log drinks. | Manual logging may be inconvenient during a social outing. | Summaries and insights become incomplete. | 4 | 3 | 12 | Medium | Open | Keep the logging flow fast; consider reminders as a later feature. | Matthew Reid | 31 May 2026 | Validate in interviews.
R03 | Venue/Menu Data | Venue and menu data is hard to maintain. | Live venue data and prices may change often. | Data may become inaccurate or outdated. | 4 | 4 | 16 | High | Open | Use sample or limited realistic data for MVP; avoid promising live coverage. | Matthew Reid | 14 Jun 2026 | Important technical/business risk.
R04 | AI Insights | AI insights feel judgemental or generic. | Poor wording or weak logic may reduce trust. | Users may ignore or dislike the feature. | 3 | 4 | 12 | Medium | Open | Use supportive wording, no medical claims, and insights based on clear logged patterns. | Matthew Reid | 31 May 2026 | Test example wording.
R05 | Responsible Design | Alcohol-related features are misunderstood as encouraging drinking. | Venue discovery, menus or social features may appear promotional. | App could conflict with responsible design goals. | 3 | 5 | 15 | High | Open | Avoid leaderboards, gamified consumption and wording that encourages drinking more. | Matthew Reid | 28 Jun 2026 | High importance due to subject matter.
R06 | Data/Privacy | Privacy concerns reduce user adoption. | Users may not want to share location, venue or drinking data. | Users may avoid logging real information. | 3 | 4 | 12 | Medium | Open | Minimise data collection; allow simple use; make data purpose clear. | Matthew Reid | 28 Jun 2026 | Assess during UX/UI design.
R07 | Technical | Map or venue discovery integration is harder than expected. | APIs, permissions or platform differences may add complexity. | Technical setup and build phases may slip. | 3 | 4 | 12 | Medium | Open | Start with sample venue data and simple map/list approach. | Matthew Reid | 12 Jul 2026 | Avoid over-engineering MVP.
R08 | Business Model | Premium features are not compelling enough. | Users may not see value in paying for advanced insights. | Freemium model may need revision. | 3 | 3 | 9 | Medium | Monitoring | Keep premium placeholders light in MVP and validate willingness to pay. | Matthew Reid | 14 Jun 2026 | Business model can evolve later.
R09 | Timeline | Research feedback takes longer than expected. | Finding participants may be slower than planned. | MVP scope and backlog planning may be delayed. | 3 | 3 | 9 | Medium | Monitoring | Use a small sample target and continue with best available feedback. | Matthew Reid | 31 May 2026 | Early project risk.
R10 | Technical | Cross-platform build choice delays development. | Need to select and configure a suitable iOS/Android stack. | Core feature build may start late. | 2 | 4 | 8 | Medium | Open | Make stack decision during technical setup phase and keep first build simple. | Matthew Reid | 12 Jul 2026 | Review after UX/UI phase.

## Risk Matrix
Risk Matrix — Likelihood × Impact
Likelihood \ Impact | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
Priority
High | 15–25 | Actively Reduce
Medium | 8–14 | Monitor and Mitigate
Low | 1–7 | Track

## Lists
Status | Risk Status | Category | Owner | Likelihood | Impact
Not Started | Open | User Research | Matthew Reid | 1 | 1
In Progress | Monitoring | Product Scope | TBC | 2 | 2
Validated | Mitigated | Technical |  | 3 | 3
Invalidated | Closed | Data/Privacy |  | 4 | 4
Needs Review | Accepted | Responsible Design |  | 5 | 5
Business Model
Timeline
Venue/Menu Data
AI Insights