## Dashboard
Drink Awareness App — Feature Backlog Dashboard
Purpose: Track all MVP and future features with priority, effort, value and status. Updated 18 June 2026 with research findings.
Total Items |  | MVP Items |  | Must Have |  | Done | Not Started
51 |  | 42 |  | 29 |  | 0 | 50
ID | Epic | Feature / Task | MoSCoW | Phase | Priority Score | Added
DAA-047 | Drink Logging | Quick-select preset drinks on Log Drink screen | Must | Core feature build | 14 | Research 18 Jun 2026
DAA-048 | Drink Logging | Revise required fields: drink name and time only | Must | Core feature build | 14 | Research 18 Jun 2026
DAA-049 | AI Insights | Every insight must show what data it is based on | Must | Core feature build | 14 | Research 18 Jun 2026
DAA-050 | App Foundation | Local-first, no account required on first launch | Must | Core feature build | 13 | Research 18 Jun 2026
DAA-005 | App Foundation | Add non-medical disclaimer | Must | Core feature build |  | Original
DAA-018 | Drink Logging | Manual custom drink entry | Must | Core feature build |  | Original
DAA-023 | Summaries | Build daily summary screen | Must | Core feature build |  | Original
DAA-024 | Summaries | Build weekly summary screen | Must | Core feature build |  | Original
DAA-028 | AI Insights | Generate/display basic insight | Must | Core feature build |  | Original

## Feature Backlog
Feature Backlog — 50 items (42 MVP, 8 Future) — Updated 18 June 2026
ID | Epic | Feature / Task | User Need | MVP Status | MoSCoW | Phase | Status | Effort (1-5) | Value (1-5) | Risk (1-5) | Priority Score | Dependencies | Acceptance Criteria | Notes
DAA-001 | App Foundation | Confirm technical stack and architecture | A maintainable app foundation is needed before development begins. | MVP | Must | Technical setup | Not Started | 2 | 5 | 2 | 11 | Product brief, MVP scope | Architecture and core technologies are documented and agreed. | Keep cross-platform iOS/Android goal in mind.
DAA-002 | App Foundation | Create mobile app project structure | Developers need a clean starting point for implementation. | MVP | Must | Technical setup | Not Started | 2 | 5 | 2 | 11 | DAA-001 | Project builds successfully and includes organised folders/modules.
DAA-003 | App Foundation | Implement core navigation | Users need to move between venues, logging, summaries and insights. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-002 | Main navigation works across all MVP screens.
DAA-004 | App Foundation | Add age 18+ positioning/onboarding notice | Users should understand the app is for adults only. | MVP | Should | Core feature build | Not Started | 1 | 4 | 2 | 11 | DAA-003 | App clearly states it is intended for adults aged 18+. | Responsible design requirement.
DAA-005 | App Foundation | Add non-medical disclaimer | Users need clear messaging that the app is not medical advice. | MVP | Must | Core feature build | Not Started | 1 | 5 | 2 | 12 | DAA-003 | Disclaimer is visible in onboarding, settings or relevant insight areas.
DAA-006 | Venue Discovery | Create sample venue data model | The app needs venue data for discovery and details screens. | MVP | Must | Technical setup | Not Started | 2 | 5 | 2 | 11 | DAA-001 | Venue data model supports name, location, description and venue type. | Sample data acceptable for MVP.
DAA-007 | Venue Discovery | Build venue list screen | Users need a simple way to browse example venues. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-006 | Users can view a list of venues with key details.
DAA-008 | Venue Discovery | Build venue search | Users need to quickly find venues by name or category. | MVP | Should | Core feature build | Not Started | 2 | 4 | 2 | 10 | DAA-007 | Users can search/filter venue list using simple text input.
DAA-009 | Venue Discovery | Add map/list venue discovery view | Users may expect a map-based discovery experience. | MVP | Must | Core feature build | Not Started | 4 | 5 | 3 | 8 | DAA-006 | Users can browse venues using a map and/or list interface. | Map implementation can be simplified if needed.
DAA-010 | Venue Discovery | Add basic venue filtering | Users may want to filter venue types or distance. | MVP | Could | Polish/testing/iteration | Not Started | 2 | 3 | 2 | 9 | DAA-007 | Users can apply at least one simple filter to venue results. | Could be moved post-MVP.
DAA-011 | Venue Details | Build venue details screen | Users need more context before logging drinks at a venue. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-006, DAA-007 | Users can open a venue and view name, location, description and drinks.
DAA-012 | Drink Menus | Create drink menu data model | The app needs drink data for menus and quick logging. | MVP | Must | Technical setup | Not Started | 2 | 5 | 2 | 11 | DAA-001 | Drink menu data supports name, category, size, ABV and price.
DAA-013 | Drink Menus | Build drink menu screen | Users need to view drink options and prices. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-011, DAA-012 | Users can view example drink menu items for a venue.
DAA-014 | Drink Menus | Show drink detail information | Users need useful details before logging a drink. | MVP | Should | Core feature build | Not Started | 2 | 4 | 2 | 10 | DAA-013 | Drink item shows name, type, size, ABV and price where available.
DAA-015 | Drink Menus | Display prices and ABV clearly | Users need to understand cost and alcohol strength. | MVP | Must | Core feature build | Not Started | 1 | 5 | 2 | 12 | DAA-013 | Price and ABV are clearly visible for sample drinks.
DAA-016 | Drink Logging | Create drink log data model | The app needs stored log entries to calculate summaries. | MVP | Must | Technical setup | Not Started | 2 | 5 | 2 | 11 | DAA-001 | Drink log data supports drink details, date/time and venue.
DAA-017 | Drink Logging | Quick log from menu item | Users need fast logging during social outings. | MVP | Must | Core feature build | Not Started | 3 | 5 | 3 | 9 | DAA-013, DAA-016 | Users can log a drink directly from a menu item.
DAA-018 | Drink Logging | Manual custom drink entry | Users need to log drinks that are not in a menu. | MVP | Must | Core feature build | Not Started | 3 | 5 | 3 | 9 | DAA-016 | Users can manually enter drink name, type, size, ABV and price. | See DAA-048 for revised required fields from research.
DAA-019 | Drink Logging | Calculate UK alcohol units | Users need awareness of alcohol quantity, not just drink count. | MVP | Must | Core feature build | Not Started | 2 | 5 | 2 | 11 | DAA-016 | App calculates units from volume and ABV using a consistent formula. | Useful portfolio feature.
DAA-020 | Drink Logging | Log optional drink price/spend | Budget-conscious users need spending visibility. | MVP | Should | Core feature build | Not Started | 2 | 4 | 2 | 10 | DAA-016 | Users can add or confirm a drink price when logging.
DAA-021 | Drink Logging | Edit or delete logged drink | Users need to fix mistakes in their logs. | MVP | Should | Polish/testing/iteration | Not Started | 2 | 4 | 2 | 10 | DAA-016 | Users can edit or delete a logged drink entry.
DAA-022 | Drink Logging | Add helpful empty states | Users need clear guidance when no drinks are logged. | MVP | Should | Polish/testing/iteration | Not Started | 1 | 3 | 1 | 11 | DAA-023, DAA-024 | Empty summary/log screens explain what to do next.
DAA-023 | Summaries | Build daily summary screen | Users need short-term awareness of drinks logged today. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-016, DAA-019 | Daily summary shows today's drinks, units and optional spending.
DAA-024 | Summaries | Build weekly summary screen | Users need pattern awareness across multiple days. | MVP | Must | Core feature build | Not Started | 3 | 5 | 2 | 10 | DAA-016, DAA-019 | Weekly summary shows basic totals and trends for the current week.
DAA-025 | Summaries | Add basic charts/visual summaries | Users may understand patterns better visually. | MVP | Should | Polish/testing/iteration | Not Started | 3 | 4 | 2 | 9 | DAA-023, DAA-024 | Daily/weekly summaries include a simple chart or visual indicator.
DAA-026 | Summaries | Add spending breakdown | Budget-conscious users need visibility of drink spending. | MVP | Should | Polish/testing/iteration | Not Started | 2 | 4 | 2 | 10 | DAA-020, DAA-023 | Summary can show estimated spending where price is available.
DAA-027 | AI Insights | Define AI insight rules/prompts | The app needs a safe basis for generated feedback. | MVP | Must | Core feature build | Not Started | 3 | 5 | 3 | 9 | Research findings | Insight logic or prompts are documented and responsible.
DAA-028 | AI Insights | Generate/display basic insight | Users need personalised awareness feedback. | MVP | Must | Core feature build | Not Started | 3 | 5 | 3 | 9 | DAA-023, DAA-024, DAA-027 | App displays at least one useful insight based on logged data. | Can start with rule-based insight if API not ready.
DAA-029 | AI Insights | Add insight safety wording | Users need feedback that is supportive and non-medical. | MVP | Must | Core feature build | Not Started | 1 | 5 | 2 | 12 | DAA-028 | Insights avoid diagnosis, shame and encouragement of excessive drinking.
DAA-030 | AI Insights | Add insight feedback controls | Users may want to dismiss or rate insights. | MVP | Could | Polish/testing/iteration | Not Started | 2 | 3 | 2 | 9 | DAA-028 | Users can dismiss or provide simple feedback on an insight. | Could be future if time is tight.
DAA-031 | Privacy & Settings | Store logged data reliably | Users need their logged drinks to persist between sessions. | MVP | Must | Technical setup | Not Started | 3 | 5 | 3 | 9 | DAA-016 | Drink logs persist locally or through chosen storage approach.
DAA-032 | Privacy & Settings | Allow data deletion | Users should have control over their personal app data. | MVP | Should | Polish/testing/iteration | Not Started | 2 | 4 | 2 | 10 | DAA-031 | Users can delete logs or reset app data.
DAA-033 | Privacy & Settings | Create basic settings screen | Users need access to disclaimers and simple preferences. | MVP | Should | Polish/testing/iteration | Not Started | 2 | 3 | 2 | 9 | DAA-003 | Settings screen includes disclaimer and optional preferences.
DAA-034 | Testing | Test alcohol unit calculation | The app must calculate summaries correctly. | MVP | Must | Polish/testing/iteration | Not Started | 2 | 5 | 2 | 11 | DAA-019 | Unit calculation tests pass for multiple example drinks.
DAA-035 | Testing | Conduct small usability test | The app needs validation that users understand the flow. | MVP | Should | Polish/testing/iteration | Not Started | 3 | 4 | 2 | 9 | MVP prototype | At least a small number of users test the main flow and provide feedback.
DAA-036 | Testing | Bug fixing and UI polish | The MVP needs to be stable and presentable. | MVP | Must | Polish/testing/iteration | Not Started | 4 | 5 | 3 | 8 | Core feature build | Critical bugs are fixed and key screens look portfolio-ready.
DAA-037 | Deployment | Create deployment checklist | Release prep needs to be tracked before portfolio launch. | MVP | Must | Deployment prep | Not Started | 2 | 4 | 2 | 10 | DAA-036 | Checklist covers build, testing, screenshots, privacy notes and release tasks.
DAA-038 | Deployment | Prepare portfolio README/screenshots | The project needs to demonstrate value to viewers. | MVP | Must | MVP deployment / portfolio-ready release | Not Started | 2 | 5 | 2 | 11 | DAA-036 | GitHub README includes overview, screenshots, features and setup notes.
DAA-047 | Drink Logging | Quick-select preset drinks on Log Drink screen | Users need to log drinks in seconds during a social outing without entering details manually. | MVP | Must | Core feature build | Not Started | 2 | 5 | 1 | 12 | DAA-018 | User can tap a preset (e.g. Pint of Lager, Glass of Wine) and log it in one or two taps. | ADDED: Research 18 Jun 2026. Most-requested finding. Include: pint lager, pint cider, glass wine, bottled beer, single spirit, double spirit, cocktail.
DAA-048 | Drink Logging | Revise required fields: drink name and time only | Users should not be required to enter more than the minimum needed to log a drink. | MVP | Must | Core feature build | Not Started | 1 | 5 | 1 | 13 | DAA-018, DAA-047 | Required fields on Log Drink are drink name/type and time only. All other fields are optional. | ADDED: Research 18 Jun 2026. Only drink name (6/8) and time (4/8) had majority support. ABV must never be required.
DAA-049 | AI Insights | Every insight must show what data it is based on | Users need to understand the basis of an insight before they can trust it. | MVP | Must | Core feature build | Not Started | 1 | 5 | 1 | 13 | DAA-028 | Every insight card includes a note explaining what data it is based on. | ADDED: Research 18 Jun 2026. Trust factor rated 7/8. Non-negotiable implementation requirement.
DAA-050 | App Foundation | Local-first, no account required on first launch | Users should be able to use the app immediately without creating an account. | MVP | Must | Core feature build | Not Started | 1 | 4 | 1 | 12 | DAA-031 | App can be used fully without account creation. No forced sign-up on first launch. | ADDED: Research 18 Jun 2026. Elevated from Should to Must. 7/8 comfortable with no account.
DAA-039 | Future Feature | Drink photo recognition | Users may want faster logging through a photo. | Future | Could | Post-MVP | Not Started | 5 | 4 | 5 | 4 | Stable logging flow | Future feature documented. | Requires image recognition.
DAA-040 | Future Feature | Friend groups | Users may want private social accountability. | Future | Could | Post-MVP | Not Started | 4 | 3 | 4 | 5 | Privacy design | Future feature documented. | Must avoid encouraging excess.
DAA-041 | Future Feature | Social accountability / leaderboard | Some users may want social motivation, but it is risky. | Future | Won't | Post-MVP | Not Started | 5 | 2 | 5 | 2 | Responsible design review | Feature remains excluded unless redesigned safely. | Avoid ranking by alcohol consumed.
DAA-042 | Future Feature | Goal streaks | Users may want personal goals and progress streaks. | Future | Could | Post-MVP | Not Started | 3 | 3 | 3 | 7 | Summaries and settings | Future feature documented. | Focus on alcohol-free days rather than consumption.
DAA-043 | Future Feature | Smarter recommendations | Users may want lower-alcohol or cheaper recommendations. | Future | Could | Post-MVP | Not Started | 4 | 4 | 4 | 6 | More user data | Future feature documented.
DAA-044 | Future Feature | Venue partnership dashboard | Venues may later want verified menus or analytics. | Future | Won't | Post-MVP | Not Started | 5 | 3 | 5 | 3 | Business partnerships | Feature remains outside MVP.
DAA-045 | Future Feature | Premium subscription/payment integration | The freemium model may need payment support later. | Future | Won't | Post-MVP | Not Started | 5 | 4 | 5 | 4 | Premium feature validation | Payment integration is deferred.
DAA-046 | Future Feature | Real venue API integration | The app may later pull live venue/menu data. | Future | Could | Post-MVP | Not Started | 5 | 4 | 5 | 4 | Technical feasibility | Future integration options researched after MVP.

## User Stories
User Stories — Updated 18 June 2026
Story ID | Epic | User Story | Acceptance Criteria | Linked Backlog IDs | Priority
US-001 | Venue Discovery | As a social drinker, I want to browse nearby/example venues so that I can choose where I may log drinks. | Venue list or map is visible and each venue can be opened. | DAA-007, DAA-009, DAA-011 | Must
US-002 | Drink Menus | As a user, I want to view drink names, ABV and prices so that I can make more informed choices. | Menu shows sample drinks with useful details. | DAA-012, DAA-013, DAA-015 | Must
US-003 | Drink Logging | As a user, I want to log a drink quickly so that I can track consumption during a social outing. | User can log from a menu item or manual entry form. | DAA-017, DAA-018 | Must
US-004 | Drink Logging | As a user, I want the app to estimate alcohol units so that I can understand more than just drink count. | Logged drinks calculate units consistently from size and ABV. | DAA-019 | Must
US-005 | Summaries | As a user, I want a daily summary so that I can see what I have logged today. | Today's drinks, units and optional spending are displayed. | DAA-023 | Must
US-006 | Summaries | As a user, I want a weekly summary so that I can spot patterns across several days. | Weekly totals and basic visual summary are displayed. | DAA-024, DAA-025 | Must
US-007 | AI Insights | As a user, I want supportive insights so that I can reflect on my drinking habits without feeling judged. | At least one insight is shown and uses non-medical wording. | DAA-027, DAA-028, DAA-029 | Must
US-008 | Privacy & Settings | As a user, I want privacy and control so that I feel safe using the app. | App avoids unnecessary data collection and allows deletion/reset. | DAA-031, DAA-032 | Should
US-009 | Portfolio | As a portfolio viewer, I want to understand the project quickly so that I can see the product value. | README includes purpose, screenshots, features and setup information. | DAA-038 | Must
US-010 | Drink Logging | As a user, I want to select a drink from a quick-select list so that I can log it in a few seconds. | Preset list visible on Log Drink screen. Tapping a preset logs it with minimal additional input. | DAA-047 | Must
US-011 | Drink Logging | As a user, I want drink name and time to be the only required fields so that logging never feels like a chore. | Log Drink form completes successfully with only name and time. All other fields shown as optional. | DAA-048 | Must
US-012 | AI Insights | As a user, I want every AI insight to tell me what data it is based on so that I can decide whether to trust it. | Every displayed insight includes a visible note explaining its data basis. | DAA-049 | Must

## Release Plan
Release Plan — Updated 18 June 2026
Phase | Date Range | Main Focus | Key Outputs | Related Backlog Items | Status
Research and validation | 18 May – 31 May 2026 | Validate problem, users, competitors and assumptions. | Research plan, interview questions, competitor analysis, survey findings. | DAA-035, research inputs | Done
Planning and backlog | 1 Jun – 18 Jun 2026 | Turn project scope into tasks and prioritised build plan. | MVP scope, feature backlog updated with research findings. | All backlog items | Done
UX/UI design | 15 Jun – 28 Jun 2026 | Design core app screens and user flows. | Wireframes, navigation flow, screen designs. | DAA-003, DAA-007, DAA-011, DAA-013, DAA-018, DAA-023, DAA-024, DAA-028, DAA-047 | In Progress
Technical setup | 29 Jun – 12 Jul 2026 | Set up app structure, data models and core architecture. | Project setup, data models, storage approach. | DAA-001, DAA-002, DAA-006, DAA-012, DAA-016, DAA-031 | Not Started
Core feature build | 13 Jul – 23 Aug 2026 | Build MVP screens and core functionality. | Venue discovery, logging, summaries, insights, presets. | DAA-003 to DAA-030, DAA-047 to DAA-050 | Not Started
Polish, testing, iteration | 24 Aug – 20 Sep 2026 | Improve usability, fix bugs and validate with users. | Charts, edit/delete, testing, bug fixes. | DAA-010, DAA-021 to DAA-026, DAA-030, DAA-032 to DAA-036 | Not Started
Deployment prep | 21 Sep – 4 Oct 2026 | Prepare app and repo for release/demo. | Checklist, final testing, release preparation. | DAA-037 | Not Started
MVP deployment / portfolio release | 5 Oct – 18 Oct 2026 | Create final portfolio-ready release. | README, screenshots, release notes. | DAA-038 | Not Started
Post-MVP | After 18 Oct 2026 | Evaluate future ideas after first version is validated. | Future backlog review. | DAA-039 to DAA-046 | Deferred

## Prioritisation Guide
Feature Backlog — Prioritisation Guide
Field | Meaning | How to Use | Example
MVP Status | Whether the item belongs in the first build or future backlog. | Use MVP for first version work; Future for post-MVP ideas. | MVP
MoSCoW | Must, Should, Could, Won’t for MVP prioritisation. | Must items are required for MVP completion. | Must
Effort (1-5) | Estimated work required. | 1 is small/easy; 5 is large/complex. | 3
Value (1-5) | Expected value to users/project. | 1 is low value; 5 is high value. | 5
Risk (1-5) | Uncertainty, technical complexity or responsible design risk. | 1 is low risk; 5 is high risk. | 2
Priority Score | Formula: Value - Effort - Risk + 10. | Higher score = stronger candidate for earlier delivery. | Calculated
Status | Current progress on this item. | Update throughout the build phase. | Not Started
Dependencies | Other items needed before this one can start. | Use IDs so dependencies remain clear. | DAA-016

## Lists
MVP Status | MoSCoW | Phase | Status
MVP | Must | Research and validation | Not Started
Future | Should | Planning and backlog | In Progress
| Could | UX/UI design | Blocked
| Won't | Technical setup | Done
|  | Core feature build | Deferred
Polish/testing/iteration
Deployment prep
MVP deployment / portfolio-ready release
Post-MVP